## Gantt Chart
Milestone Billing Template | [51 empty] | #VALUE!
| PROJECT NAME |  |  | [Example Project]
| PROJECT NUMBER |  |  | [########]
| CONTRACT VALUE |  |  | 400000 | Update the Contract Value
# | PHASE NAME | MILESTONE | FEE % | AMOUNT | DUE DATE | INVOICE PAID (Y/N) | JAN |  |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  |  | JUN |  |  |  | JUL |  |  |  | AUG |  |  |  |  | SEP |  |  |  | OCT |  |  |  |  | NOV |  |  |  | DEC
 | time axis 2025-01-03 to 2025-12-26
1 | Pre-Design |  | 5% | 20000
|  | 1 | 25% | 6666.6667 | 2025-01-03 | Y | bar: 2025-01-03
|  | 2 | 50% | 5000 | 2025-01-31 | Y | bar: 2025-01-31
|  | 3 | 100% | 8333.3333 | 2025-02-28 | Y | bar: 2025-02-28
2 | Schematic Design |  | 15% | 60000
|  | 1 | 30% | 18000 | 2025-03-14 | Y | bar: 2025-03-14
|  | 2 | 60% | 18000 | 2025-04-04 | Y | bar: 2025-04-04
|  | 3 | 100% | 24000 | 2025-04-25 | N | bar: 2025-04-25
3 | Design Development |  | 15% | 60000
|  | 1 | 30% | 18000 | 2025-05-16 | N | bar: 2025-05-16
|  | 2 | 60% | 18000 | 2025-06-06 | N | bar: 2025-06-06
|  | 3 | 100% | 24000 | 2025-06-27 | N | bar: 2025-06-27
4 | Construction Document |  | 40% | 160000
|  | 1 | 30% | 48000 | 2025-07-18 | N | bar: 2025-07-18
|  | 2 | 60% | 48000 | 2025-08-08 | N | bar: 2025-08-08
|  | 3 | 100% | 64000 | 2025-08-29 | N | bar: 2025-08-29
5 | Construction Administration |  | 25% | 100000
|  | 1 | 20% | 20000 | 2025-09-12 | N | bar: 2025-09-12
|  | 2 | 40% | 20000 | 2025-10-10 | N | bar: 2025-10-10
|  | 3 | 60% | 20000 | 2025-11-07 | N | bar: 2025-11-07
|  | 4 | 80% | 20000 | 2025-12-05 | N | bar: 2025-12-05
|  | 5 | 100% | 20000 | 2025-12-26 | N | bar: 2025-12-26
[7 empty] | I = Invoice Created |  |  |  |  | S = Invoice Sent |  |  |  | F = Future Invoice
| INSTRUCTIONS: | Update the contract amount at the top
Update the fee % for each phase
Adjust the milstones and percentages as needed to meet your project schedule. You may have to adjust the calculations based on the new percentages.
Assign a due date for each milestone
Build out the invoicing schedule on the Gantt Chart with "F" for future invoices
As you progress through the project, change the Fs to I when an invoice is created, and an S when an invoice is sent
As invoices are paid, put a Y in column G
| #VALUE! | Learn more about how your firm can improve performance with BQE CORE